## Initial Parameters
## Initial Parameters
Date | 2025-09-22 | (auto-set to today)
Project Name | RodWal Terminal — Quant Research & Retail Investment Decision Support
Sponsor/Cost Authority | RodWal Capital Strategies
Customer Name | Internal / Pilot Users
Time frame (WKs) | 16
Initial Date | 2025-09-22 | Editable
Due Date | 2026-01-12 | Calculated = Initial Date + (Weeks*7)
Development Rate (Internal) | 20 | Set your hourly rate and currency
Currency | USD | Change to HNL, MXN, etc. if needed

## Technical justification
## Technical justification
Element | Justification
Python + Tkinter | Lightweight, native desktop UI with minimal dependencies; ideal for an offline-capable terminal shell and fast iteration.
pandas + numpy | Core time-series and numerical stack for quote handling, portfolio analytics, factor construction, and risk metrics.
yfinance (Yahoo Finance) | Free, delayed market data suitable for prototypes and research; easily swappable with paid providers via an abstraction layer.
Provider Abstraction (data_providers) | Enables switching between Yahoo/Polygon/Tiingo/TwelveData without refactoring UI modules.
SQLite / PostgreSQL | SQLite for local cache and portability; PostgreSQL for multi-user, auditability, and scaling of historical data and results.
Job Scheduler (APScheduler) | Periodic tasks for quotes refresh, news polling, and overnight batch factors without blocking the UI thread.
Caching (optional Redis) | Faster repeat queries, rate-limit protection, and smoother UX when auto-refresh is enabled.
Packaging (PyInstaller) | Single-file or folder-based installer for Windows/macOS; simplifies pilot distribution to internal users.
Testing (pytest) | Unit/integration tests for symbol normalization, pricing pipelines, portfolio math, and screeners to ensure correctness.
Logging + Telemetry | Structured logs and optional anonymous telemetry to support troubleshooting and usage insights during the pilot.

## Project Schedule
## Project Schedule
Phase | Duration | Key Activities | Owners
1. Discovery & Architecture | Weeks 1–2 | Requirements; architecture; repo/CI; coding standards; risk register; success metrics. | Tech Lead, Architect, Quant Lead
2. Market Data & Watchlist | Weeks 3–4 | Batch quote service; normalization/aliases; TTL caching; config storage; MKT view with colorized table. | Backend, Data Eng
3. UI Shell & Router | Weeks 3–5 | Command router; async loaders; status/spinner; keyboard mnemonics; theming. | Frontend (Tk), Tech Lead
4. Portfolio & Risk | Weeks 5–8 | CSV import; valuation; P/L; weights; vol/Sharpe/ES; stress scenarios; persistence. | Backend, Quant, QA
5. Screener & Factors | Weeks 7–10 | Momentum (12-1), size, low-vol; filter builder; save/load screens; export. | Quant, Backend
6. Charts & Symbol Card | Weeks 8–12 | Sparklines; symbol card with 5D/1M/1Y performance; 52w H/L; basic fundamentals. | Frontend, Backend
7. News & Econ Calendar | Weeks 10–14 | RSS ingestion; keyword tagging; today/this-week calendar; local timezone. | Backend, QA
8. QA, Docs & Packaging | Weeks 14–16 | Test suites; user/tech docs; installer builds; pilot rollout; feedback loop. | QA, DevOps, Tech Writer

## Development Quote
## Development Quote
Module | Feature | Type | Est HRs | Rate | Est. Cost
Foundations | Repo/CI, logging, config, theming | Engineering |  | 20 | 0
Markets | Batch quotes, aliases, caching, MKT view | Feature |  | 20 | 0
Portfolio | Valuation, P/L, risk (vol, Sharpe, ES) | Feature |  | 20 | 0
Screener | Filters + factors (momentum, size, low-vol) | Feature |  | 20 | 0
Charts | Sparklines + symbol card | Feature |  | 20 | 0
News/Econ | RSS + economic calendar | Feature |  | 20 | 0
Docs | User guide + technical docs | Documentation |  | 20 | 0
QA & Packaging | Tests, installer, pilot rollout | Engineering |  | 20 | 0
|  |  |  | Total: | 0

## APP Blueprint
## APP Blueprint
Folder Structure |  |  | Description
rodwal_terminal/ |  | (Project Root) | Main application directory
| core/ | __init__.py | Initialization file for core module
|  | theme.py | Stores Terminal's colour palette
|  | config.py | Application settings and configuration
|  | logging.py | Logging setup and configuration
|  | scheduler.py | Periodic job scheduler
|  | helper_extensions.py | Stores helper functions (e.i Format $T, $B, $M..)
| data_providers/ | __init__.py | Initialization file for data providers
|  | base.py | Base class for market data APIs
|  | yahoo.py | Yahoo Finance integration
|  | FinancialModelingPrep.py | FMP API Integration
|  | polygon.py (optional) | Polygon.io integration
| modules/ | __init__.py | Initialization file for domain modules
|  | markets.py | Market overview and data logic
|  | charts.py | Displays financial information in charts
|  | portfolio.py | Portfolio management logic
|  | screener.py | Stock screener functionality
|  | news.py | News aggregation and processing
|  | econ.py | Economic indicators and data
| ui/ | terminal.py | Tkinter shell and command router
|  | views/ | UI views and widgets
|  | views/*.py | Individual view components
| config/ | markets.json | Market watchlist configuration
|  | portfolio.json | Portfolio configurations (Depoits Phasing & Resource allocation)
|  | settings.json | User preferences and settings
| tests/ | test_*.py | Unit and integration tests

## Deliverables
## Deliverables
Category | Deliverable | Description
Codebase | rodwal_terminal/ source | Core, modules, providers, UI, tests
Configuration | settings.json, markets.json | User-configurable paths, refresh intervals, watchlist
Executable | Installer (PyInstaller) | Signed build for Windows/macOS for pilot users
Documentation | User Guide | Commands, workflows, screenshots
Documentation | Technical Guide | Architecture, data provider interfaces, deployment
Quality | Test Suite | Unit/integration tests with coverage report
Operations | Runbook | Logging, troubleshooting, update/rollback procedures
Analytics | Sample Screeners & Reports | Saved filters, factor definitions, and example outputs